## Risk Register
Risk Register
Product: [Your Product Name] ¦ Sprint/Release: [Current] ¦ Last Updated: [Date]
ID | Feature / Module | Risk Statement | Likelihood (1-3) | Impact (1-3) | Risk Score | Tier | Mitigating Tests | Owner | Status | Last Reviewed
R-001 | Checkout / Payment | Payment gateway timeout under load causes duplicate charges | 3 | 3 | 9 | T1 | TC-101, TC-102, TC-103 EXP-01: Payment load scenario | Sarah K. | Active | 2026-02-28
R-002 | Authentication | Session token not invalidated on password change allows stale access | 2 | 3 | 6 | T1 | TC-201, TC-202 TC-203: Token lifecycle | James M. | Active | 2026-02-28
R-003 | Order Fulfilment | Inventory sync lag causes overselling during flash sales | 3 | 2 | 6 | T1 | TC-301, TC-302 EXP-02: Concurrent order scenario | Sarah K. | Active | 2026-02-28
R-004 | Search / Filtering | Search index rebuild fails silently after catalogue update | 2 | 2 | 4 | T2 | TC-401: Index rebuild verification TC-402: Stale results check | Priya L. | Monitoring | 2026-02-28
R-005 | User Profile | Display name change not reflected across cached pages | 1 | 1 | 1 | T3 | TC-501: Profile update smoke | James M. | Active | 2026-02-14
R-006 | Reporting Dashboard | Monthly report export times out for accounts with 50k+ transactions | 2 | 2 | 4 | T2 | TC-601: Large dataset export TC-602: Timeout handling | Priya L. | Active | 2026-02-28
R-007 | Email Notifications | Transactional emails delayed or dropped by third-party provider | 2 | 3 | 6 | T1 | TC-701: Email delivery check TC-702: Retry/fallback path | Sarah K. | Active | 2026-02-28
R-008 | Admin Panel | Bulk user import CSV parsing fails on special characters | 1 | 2 | 2 | T3 | TC-801: CSV edge cases | James M. | Active | 2026-02-14
R-009 | Mobile Responsiveness | Cart layout breaks on tablets in landscape orientation | 1 | 1 | 1 | T3 | TC-901: Responsive smoke (tablet) | Priya L. | Low Priority | 2026-02-14
R-010 | API Gateway | Rate limiting config change causes legitimate requests to be throttled | 3 | 3 | 9 | T1 | TC-1001, TC-1002 EXP-03: Load ramp scenario TC-1003: Config validation | Sarah K. | Active | 2026-02-28

## Risk Matrix
Risk Assessment Matrix
IMPACT → | 1 - Minor | 2 - Significant | 3 - Severe
3 - Very Likely | 3 | 6 | 9
2 - Moderate | 2 | 4 | 6
1 - Unlikely | 1 | 2 | 3
LIKELIHOOD ↑
Tier Mapping
Score 6-9 | Tier 1 (High) | Deep testing: negative cases, boundaries, integration, exploratory
Score 3-4 | Tier 2 (Medium) | Standard testing: happy path + key boundaries + basic integration
Score 1-2 | Tier 3 (Low) | Baseline only: smoke-level checks
Scoring Guide
Score | Likelihood Meaning | Impact Meaning
1 | Unlikely to fail. Stable code, few changes, well-understood. | Minor inconvenience. Cosmetic or low-usage feature.
2 | Moderately likely. Some complexity, recent changes, or known fragility. | Significant impact. Affects key workflows or notable user group.
3 | Very likely to fail. New/complex code, frequent changes, past defects. | Severe business impact. Revenue, data, compliance, or reputation at risk.

## Test Traceability
Risk-to-Test Traceability
Risk ID | Risk Statement (Summary) | Tier | Test ID | Test Description | Result | Notes
R-001 | Duplicate charges under load | T1 | TC-101 | Payment gateway timeout handling | Pass
R-001 |  |  | TC-102 | Duplicate transaction detection | Pass
R-001 |  |  | TC-103 | Payment retry logic validation | Pass
R-001 |  |  | EXP-01 | Exploratory: payment under simulated load | Pass | Found minor logging gap, logged as low sev
R-002 | Stale session after password change | T1 | TC-201 | Session invalidation on password reset | Pass
R-002 |  |  | TC-202 | Multi-device session handling | Fail | Token persists on secondary device. Bug raised.
R-002 |  |  | TC-203 | Token lifecycle expiry | Pass
R-007 | Email delivery failures | T1 | TC-701 | Transactional email delivery verification | Pass
R-007 |  |  | TC-702 | Email retry and fallback path | Blocked | Staging email provider down
R-010 | Rate limiting misconfiguration | T1 | TC-1001 | Rate limit threshold validation | Pass
R-010 |  |  | TC-1002 | Legitimate traffic not throttled | Pass
R-010 |  |  | EXP-03 | Exploratory: gradual load ramp | Pass
R-003 | Inventory overselling | T2 | TC-301 | Inventory sync delay check | Pass
R-003 |  |  | TC-302 | Concurrent order race condition | Not Run | Awaiting test data setup
R-004 | Search index silent failure | T2 | TC-401 | Index rebuild verification after update | Pass
R-004 |  |  | TC-402 | Stale search results detection | Pass
R-005 | Profile cache staleness | T3 | TC-501 | Profile update smoke test | Pass
R-009 | Cart layout on tablets | T3 | TC-901 | Responsive layout smoke (tablet landscape) | Pass

## Minimum Baseline
Minimum Baseline Test Suite (Always Run)
These tests are non-negotiable. They execute every release, every time, regardless of scope or pressure.
Test ID | Area | Test Description | Type | Est. Duration
BL-001 | Build / Deploy | Application starts without errors, health check returns 200 | Smoke | 2 min
BL-002 | Authentication | Login with valid credentials, verify session created | Smoke | 2 min
BL-003 | Navigation | Main menu links load without errors | Smoke | 3 min
BL-004 | Checkout | Complete purchase happy path (add to cart → payment → confirmation) | Happy Path | 5 min
BL-005 | Search | Basic keyword search returns relevant results | Happy Path | 2 min
BL-006 | User Profile | View and save profile changes | Happy Path | 3 min
BL-007 | Reporting | Generate and download a standard report | Happy Path | 3 min
BL-008 | Email | Trigger a transactional email, verify delivery | Happy Path | 3 min
BL-009 | Admin Panel | Admin login and basic CRUD operation | Smoke | 3 min
BL-010 | API Health | Core API endpoints return expected status codes | Smoke | 2 min
|  |  | Total: | ~28 min